## Project Planner
GANTT - WSB Remote
| Plan Duration |  |  | Actual Start |  |  | % Complete |  |  |  | Actual (beyond plan) | [5 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | Calendar Week | [8 empty] | Schulferien
[6 empty] | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Project planning and misc. management | 8 | 2 | 9 | 1 | 100%
Generate Symbols and Footprints for PCB | 9 | 1 | 8 | 2 | 100%
Schematics for PCB | 9 | 2 | 9 | 0 | 50%
Layout for PCB | 11 | 1 | 0 | 0 | 0%
Case Prototype for Remote | 11 | 2 | 0 | 0 | 0%
PCB finalization & order | 12 | 1 | 0 | 0 | 0%
PCB assembly & commissioning | 14 | 1 | 0 | 0 | 0%
case finalization and order | 15 | 1 | 0 | 0 | 0%
nRF24 test and abstraction | 13 | 1 | 0 | 0 | 0%
LIS2HH12 abstraction | 16 | 1 | 0 | 0 | 0%
test acceleromter as counter trigger | 16 | 5 | 0 | 0 | 0%
Firmware finalization | 17 | 5 | 0 | 0 | 0%
finalize documentation | 22 | 3 | 0 | 0 | 0%
prepare presentation PP | 23 | 2 | 0 | 0 | 0%
self rating | 24 | 1 | 0 | 0 | 0%
Hand in | 25 | 1 | 0 | 0 | 0%
Documentation (Main Body, Journal) | 8 | 17 | 8 | 0 | 10%
2-week plans | 8 | 17 | 9 | 0 | 0%
First milestone meeting | 14 | 1 | 0 | 0 | 0%
Second milestone meeting | 21 | 1 | 0 | 0 | 0%